i

AGONA EAST DISTRICT ASSEMBLY

REVISED

ANNUAL ACTION PLAN FOR 202

2

PREPARED BY:

THE DPCU

AGONA EAST DISTRICT ASSEMBLY

BOX 9, AGONA NSABA

JULY

, 202

2

AGONA EAST DISTRICT ASSEMBLY

In case of reply the number and the    	                     OFFICE OF THE AGONA EAST

Date of this letter should be quoted  	 	                   DISTRICT ADMINISTRATION

Telephone: 0332020683                                             Post Office Box 9

Fax:              0332020683 	  	                                  Agona Nsaba

Our Ref:   AEDA/A.63/V.2/3

Your Ref:

# Date: 26th July, 2022

SUBMISSION OF 2022 ANNUAL ACTION PLAN  FOR AGONA EAST DISTRICT ASSEMBLY

We submit herewith the Annual Action Plan for the year 2022 for Agona East District Assembly for your perusal and consideration.

Thank you.

FOR: DISTRICT CO-ORDINATING DIRECTOR

(ALHASSAN MOHAMMED)

DISTRICT CO-ORD.DIRECTOR

THE DIRECTOR GENERAL

NATIONAL DEVELOPMENT PLANNING COMMISSION

ACCRA

THE HON.REGIONAL MINISTER

REGIONAL CO-ORDINATING COUNCIL

CAPE COAST

Attention:   REGIONAL ECONOMIC PLANNING OFFICER

REGIONAL CO-ORDINATING COUNCIL

CAPE COAST

Cc: File

# ANNUAL PLAN OF ACTION FOR 2022

Table 1.1: Annual Action Plan for the Year 2022

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  |  | Cost |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
| Department of Trade and Industry (BAC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To support over 1000 entrepreneurs in their businesses by 31/12/2025 | Economic development | Trade, Tourism and Industrial Development | Organize entrepreneurship training on financial literacy and marketing | All area councils |  |  |  |  |  |  | 10,000 |  |  | GEA(B AC) | Mast ercar d foun datio n |
|  |  |  | Organize business counseling | District wide |  |  |  |  |  |  | 1,000.00 |  |  | GEA | CA MFE D/M aster card foun datio n |
| Facilitate access to credit for more than 500 MSMEs | Economic development | Trade, Tourism and Industrial Development | Support start-up and existing businesses with credit facilities | Nsaba Area council |  |  |  |  |  |  | 30,000.0 0 |  |  | Camfed | Mast ercar d foun datio n |
|  |  |  | Support start-up business with startup kits | All area council |  |  |  |  |  |  | 50,000.0 0 |  |  | Camfed | Mast ercar d foun datio |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | n |
| Facilitate the acquisition of over 50acreas of dedicated land banks for industrial development by 31/12/2025 | Economic development | Trade, Tourism and Industrial Development | Train small business in Management, Record keeping & Customer care | Nsaba |  |  |  |  |  | 2,00 0.00 |  |  |  | BAC | DA |
|  |  |  | Train SME in cassava processing | Duakwa |  |  |  |  |  |  | 20,000.0 0 |  |  | BAC | AED A/C AMF ED |
|  |  |  | Train SME in oil palm processing | Duakwa |  |  |  |  |  |  | 4,000.00 |  |  | BAC | AED A/C OMF ED |
|  |  |  | Organize Two business forum meeting | Okitew/Duakw a |  |  |  |  |  |  | 5,000.00 |  |  | BAC | AED A |
| Support over 500 youth in TVET by 31/12/2025 | Economic development | Trade, Tourism and Industrial Development | Train youth between the ages of 18-35 years in business startup/entrepreneurs hip | Mensakrom electoral area |  |  |  |  |  |  | 5,000 |  |  | BAC | CA MFE D |
|  |  |  | Train youth and Adult in Agric in Alternative livelihood | District wide |  |  |  |  |  |  | 3,000.0 0 |  |  | Agric | BA C/A ED |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
|  |  |  | program |  |  |  |  |  |  |  |  |  |  |  | A |
| Support the tourism industry as a viable economic sector for development by 31/12/2025 | Economic development | Trade, Tourism and Industrial Development | Conduct exhibitions of locally produced artifacts | District wide |  |  |  |  |  |  | 5,000.00 |  |  | BAC | NBS SI |
| Department of Agriculture |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ensure the improvement of extension services to farmers by 31/12/2025 | Economic development | Agricultural Development | Support extension service delivery with logistics | District Wide |  |  |  |  | 5,000.0 0 |  | 15,000.0 0 |  |  | Dept. of Agric. | A.E. D.A. |
|  | Economic development | Agricultural Development | Conduct routine home & farm visits | District Wide |  |  |  |  | 8,800.0 0 |  | 78,800.0 0 |  |  | Dept. of Agric. | A.E. D.A |
|  | Economic development | Agricultural Development | Conduct monthly technical and management review meetings | District Wide |  |  |  |  | 5,000.0 0 |  | 5,000.00 |  |  | Dept. of Agric. | A.E. D.A |
| Improve vegetable farming by 20% by 31/12/2025 (LED) | Economic development | Agricultural Development | Conduct 30 training and demonstration sessions on GAPs in vegetable production, storage and marketing | District Wide |  |  |  |  | 5,000.0 0 |  | 20,000.0 0 |  |  | Dept. of Agric. | A.E. D.A |
|  |  |  | Conduct 15 training and | District Wide |  |  |  |  | 6,000.0 |  | 6,000.00 |  |  | Dept. of | A.E. |

| Objective |  | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
|  |  |  |  | demonstration on safe use and disposal of agro – chemicals |  |  |  |  |  | 0 |  |  |  |  | Agric. | D.A |
| Improve crop production by 40% by 31/12/2025 |  | Economic development | Agricultural Development | Support farmers with agro- chemicals and improved seeds | Nsaba area council |  |  |  |  | 5,000.0 0 |  | 20,000.0 0 |  |  | Dept. of Agric. | A.E. D.A |
|  |  |  |  | Conduct demo on control of Fall army worm | District Wide |  |  |  |  | 2,000. 00 |  | 4,000.0 0 |  |  | Dept. of Agric. | A.E. D.A |
|  |  |  |  | Distribution of chemicals for the control of FAW | District Wide |  |  |  |  | 3000. 00 |  | 1,000.0 0 |  |  | Dept. of Agric. | A.E. D.A |
|  |  |  |  | Conduct demonstratio n on conservative agric system | District Wide |  |  |  |  | 2,000. 00 |  | 2,000.0 0 |  |  | Dept. of Agric. | A.E. D.A |
| Ensure the reduction of post-harvest losses by 40% by 31/12/2025 |  | Economic development | Agricultural Development | Conduct training on post-harvest storage/handling | Nsaba area council |  |  |  |  | 1,000.0 0 |  | 10,000.0 0 |  |  | Dept. of Agric. | A.E. D.A |
| (LED) |  | Economic development | Agricultural Development | Construction of farmers market | Mankrong |  |  |  |  |  |  | 60,000.0 |  |  | Dept. of | A.E. |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
|  |  |  |  | Junction |  |  |  |  |  |  | 0 |  |  | Agric. | D.A |
| Ensure 20% of farmers achieve improved and sustainable income by 31/12/2025 | Economic development | Agricultural Development | Train farmers in agro – business and alternative agricultural practices | District wide |  |  |  |  | 1,000.0 0 |  | MAG(D ONOR) – 4,000.00 | √ |  | Dept. of Agric. | A.E. D.A |
| Ensure livestock production is improved by 30% by Dec. 2025 | Economic development | Agricultural Development | Conduct 30 training and demonstration sessions for 750 livestock farmers on GHP | District wide |  |  |  |  | 2,000.0 0 |  | MAG(D ONOR) – 10,000.0 0 |  |  | Dept. of Agric. | A.E. D.A |
|  | Economic development | Agricultural Development | Conduct 30 training and demonstration for 750 livestock farmers on feed formulation & supplementary feeding | District wide |  |  |  |  | 2,000.0 0 |  | MAG (DONOR ) – 20,000.0 0 |  |  | Dept. of Agric. | A.E. D.A |
| Ensure livestock production is improved by 30% by Dec. 2025 | Economic development | Agricultural Development | Provide routine veterinary services, prophylactic, curative and emergency management of livestock diseases and pets | District wide | √ | √ | √ | √ | 3,000.0 0 |  | MAG (DONOR ) – 40,000.0 0 |  |  | Dept. of Agric. | A.E. D.A |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
| To support the provision of climate resistant and improved seeds by Dec. 202(LED) | Economic development | Agricultural Development | Supply of improved crop varieties to farmers | Agona Nsaba |  |  |  |  | 8,000.0 0 |  | MAG(D ONOR) – 5,000.00 |  |  | Dept. of Agric. | CSIR , UCC |
|  | Economic development | Agricultural Development | Conduct training/awarene ss on mitigation of bush fire | District wide |  |  |  |  | 3,000.0 0 |  | MAG(D ONOR) – 45,000.0 0 |  |  | Dept. of Agric. | A.E. D.A, Farm ers |
|  |  |  | Conduct training/awarene ss creation on overgrazing | District wide |  |  |  |  | 3,000.0 0 |  | MAG(D ONOR) – 45,000.0 0 |  |  | Dept. of Agric. | A.E. D.A, Farm ers |
|  |  |  | Distribution of coconut and oil palm seedling (PERD) | District wide |  |  |  |  | 3,000.0 0 |  | MAG(D ONOR) – 45,000.0 0 |  |  | Dept. of Agric. | A.E. D.A, Farm ers |
|  | Economic development | Agricultural Development | Sensitize farmers against chemical disposal in water bodies | District wide |  |  |  |  | 2,000.0 0 |  | MAG(D ONOR) – 20,000.0 0 |  |  | DoA | DA, Farm ers |
| Education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To bridge the geographical access to education by 30% by 31/12/2025 | Social Services delivery | Education and youth development | Construct of 3unit Classroom blocks | Duakwa, Tawora |  |  |  |  |  |  | 784,852. 50 |  |  | GES | AED A |
|  |  |  | Complete 1 No. 6 unit classroom blocks | Obokor, Akroma,Abuak wa Akrabong Otabilkwaa |  |  |  |  | 2,840,0 00.00 |  |  |  |  | GES | GET FUN D |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
|  |  |  |  | ,Nsaba Zion Duabone, Duakwa Catholic, Mensakrom |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Completion of 3no. 3-Unit Classroom Blocks | Nsaba, Ninta, Kwesikum. |  |  |  |  | 298,753. 35 |  |  |  |  | GES | AED A |
|  |  |  | Completion of 1No. 3-Unit Classroom with ancillary facilities | AGONA KWANYAKO PRESBY JHS |  |  |  |  |  |  | 194,809.6 5 |  |  | GES | AED A |
|  |  |  | Construction of 12-Unit Toilet Block | AGONA NSABA PRESBY SHS |  |  |  |  |  |  | 274,462.9 4 |  |  | GES | GET FUN D |
|  | Social Services delivery | Education and youth development | Supply 800 dual desk to basic schools | District wide |  |  |  |  |  |  | 214,000. 00 |  |  | GES | AED A |
|  |  |  | Provide office furniture for basic schools | Selected schools |  |  |  |  |  |  | 15,000.0 0 |  |  |  |  |
|  |  |  | Organize my first day in school ceremony in all 73 KG schools | District wide |  |  |  |  | 8,000.0 0 |  |  |  |  | GES | AED A |
|  |  |  | Undertake minor repairs in 30 classroom blocks | Selected communities |  |  |  |  | 85,000. 00 |  |  |  |  | GES | AED A |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
| To improve the quality of teaching and learning by 60% by 31/12/2025 | Social Services delivery | Education and youth development | Increase the number of schools under school feeding programme | Duakwa Methodist Primary |  |  |  |  | 200,00. 00 |  |  |  |  | GES | AED A |
|  |  |  | Organize INSET on Early Childhood Education | District wide |  |  |  |  | 6,000/0 0 |  |  |  |  | GES | AED A |
|  |  |  | Provide essential supplies to schools | District wide |  |  |  |  | 13,000. 00 |  |  |  |  | GES | AED A |
| To improve the quality of teaching and learning by 60% by 31/12/2025 | Social Services delivery | Education and youth development | Organize capacitybuilding workshop for teachers on literacy and numeracy | District wide |  |  |  |  | 9,000.0 0 |  |  |  |  | GES | AED A |
|  |  |  | Organize orientation for newly trained teachers | District wide |  |  |  |  | 5,000.0 0 |  |  |  |  | GES | AED A |
|  |  |  | Provide supplementary readers to pupils | District wide |  |  |  |  | 25,000. 00 |  |  |  |  | GES | AED A |
|  |  |  | Organize enrolment drive in some 30 communities | Selected communities |  |  |  |  | 6,000.0 0 |  |  |  |  | GES | AED A |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
| To improve the quality of teaching and learning by 60% by 31/12/2025 | Social Services delivery | Education and youth development | Provide audio/visual Teaching and Learning Materials to at least five (5) schools - (Computers) | District wide |  |  |  |  | 15,000. 00 |  |  |  |  | GES | AED A |
|  |  |  | Organize examination Nitty-gritty for BECE Candidates | District wide |  |  |  |  | 5,000.0 0 |  |  |  |  | GES | AED A |
|  |  |  | Organize two mock Exams for BECE Candidates | District wide |  |  |  |  | 40,000. 00 |  |  |  |  | GES | AED A |
|  |  |  | Organize orientation for teachers on new curricula for SHS | District wide |  |  |  |  | 30,000. 00 |  |  |  |  | GES | AED A |
|  | Social Services delivery | Education and youth development | Re-train all teachers on covid protocols | District wide |  |  |  |  | 12,000. 00 |  |  |  |  | GES | GHS, AED A |
| Strengthen school management systems through the establishment | Social Services delivery | Education and youth development | Co-ordinate activities of civil society groups to advocate for girls enrolment and retention | District wide |  |  |  |  | 2,000.0 0 |  |  |  |  | GES | AED A |

| Objective of SMCs in all public schools by 31/12/2025 | Programme (PBB) | Subprogramme | Activities |  | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
|  |  |  | Organize capacity building workshop GES staff | for | DEO |  |  |  |  | 1,000.0 0 |  |  |  |  | GES | AED A |
|  |  |  | Organize training workshop SMC/PTA members in all schools | for | District wide |  |  |  |  | 9,000.0 0 |  |  |  |  | GES | AED A |
|  |  |  | Conduct regular monitoring and inspection of schools |  | District wide |  |  |  |  | 50,000. 00 |  |  |  |  | GES | AED A |
| Incorporate HIV/AIDS & Sexual reproductive health education | Social Services delivery | Education and youth development | Monitor and support school health and HIV/AIDs clubs |  | District wide |  |  |  |  | 3,500.0 0 |  |  |  |  | GES | AED A |
|  |  |  | Conduct refreshing training for peer educators and SHEP coordinators on HIV/AIDS |  | District wide |  |  |  |  | 3,500.0 0 |  |  |  |  | GES | AED A |
| Incorporate health education into teaching and learning | Social Services delivery | Education and youth development | Establish girl clubs in schools |  | District wide |  |  |  |  | 4,000.0 0 |  |  |  |  | GES | AED A |
|  |  |  | Screen children to identify their health needs |  | District wide |  |  |  |  | 5,000.0 0 |  |  |  |  | GES | AED A |

| Objective | Programme (PBB) |  | Subprogramme |  | Activities |  |  | Location |  | Time Frame |  |  |  |  |  |  |  | Cost |  |  |  |  |  | Programme Status |  |  |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  | GoG |  | IGF |  | Others |  | New |  | Ongoing |  | Lead | Colla b. |
|  |  |  |  |  | Distribute PPEs to schools |  |  | District wide |  |  |  |  |  |  |  |  |  | 8,000.0 0 |  |  |  |  |  |  |  |  |  | GES | AED A |
|  |  |  |  |  | Organize deworming programme in schools |  |  | District wide |  |  |  |  |  |  |  |  |  | 3,000.0 0 |  |  |  |  |  |  |  |  |  | GES | AED A |
|  |  |  |  |  | Monitor the observation of COVID-19 protocols |  |  | District wide |  |  |  |  |  |  |  |  |  | 3,500.0 0 |  |  |  |  |  |  |  |  |  | GES | AED A |
|  |  |  |  |  | Organize capacitybuilding workshop for SHEP coordinators on sanitation |  |  | District wide |  |  |  |  |  |  |  |  |  | 2,000.0 0 |  |  |  |  |  |  |  |  |  | GES | AED A |
| Incorporate sports and culture into teaching and learning |  |  |  |  | Organize district sports and festivals |  |  | District wide |  |  |  |  |  |  |  |  |  | 6,000.0 0 |  |  |  |  |  |  |  |  |  | GES | CNC , AED A |
|  |  |  |  |  | Provide playing equipment such as football and jerseys to schools |  |  | Selected schools |  |  |  |  |  |  |  |  |  | 90,000. 00 |  |  |  |  |  |  |  |  |  | GES | AED S |
|  |  |  |  |  | Organize District sports festival |  |  | District wide |  |  |  |  |  |  |  |  |  | 6,000.0 0 |  |  |  |  |  |  |  |  |  | GES | AED A |
| Health and Health Delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective |  | Programme (PBB) |  | Subprogramme |  | Activities | Location |  | Time Frame |  |  |  |  |  |  |  | Cost |  |  |  |  |  | Programme Status |  |  |  | Implementing Inst. |  |  |
|  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  | GoG |  | IGF |  | Others |  | New |  | Ongoing |  | Lead |  | Colla b. |
| Bridge the geographical access to health care by 31/12/2025 |  | Social Services delivery |  | Health delivery |  | Construction of CHPS compounds | Fante Bawjiase & Mankrong Junction,Duotu |  |  |  |  |  |  |  |  |  | 350,00 0.00 |  |  |  |  |  |  |  |  |  | AEDA |  | AED HD |
| Improve mental health service delivery through the provision of services in all major health facilities by 31/12/2025 |  | Social Services delivery |  | Health delivery |  | Provision of mental health service in all major health facilities | Nsaba health service |  |  |  |  |  |  |  |  |  | 265,00 0.00 |  |  |  |  |  |  |  |  |  | AEDA |  | AED HD |
|  |  |  |  |  |  | Conduct refresher training for mental health nurses | District Wide |  |  |  |  |  |  |  |  |  | 265,00 0.00 |  |  |  |  |  |  |  |  |  | AEDA |  | AED HD |
| To reduce teen pregnancy by 5% by the end of 2022 |  | Social Services delivery |  | Health delivery |  | Create awareness on the high teen pregnancy status of the district | District wide |  |  |  |  |  |  |  |  |  | 200,00 0.00 |  |  |  |  |  |  |  |  |  | DDHS/ DPHN/P HN |  | CHN S/HP O/D NO |
|  |  |  |  |  |  | Set up functional ADH centres in two sub-districts | District wide |  |  |  |  |  |  |  |  |  | 450,00 0.00 |  |  |  |  |  |  |  |  |  | DDHS/ DPHN/P HN |  | CHN S/HP O/D NO |
|  |  |  |  |  |  | Supervise activities of the adolescent health corners | District wide |  |  |  |  |  |  |  |  |  | 100,00 0.00 |  |  |  |  |  |  |  |  |  | DDHS/ DPHN/P HN |  | CHN S/HP O/D NO |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
|  |  |  | Implement the adolescent health programme | District wide |  |  |  |  | 200,00 0.00 |  |  |  |  | DDHS/ DPHN/P HN | CHN S/HP O/D NO |
|  |  |  | Train adolescent care providers in AHDS | District wide |  |  |  |  | 160,00 0.00 |  |  |  |  | DDHS/ DPHN/P HN | CHN S/HP O/D NO |
| Reduce noncommunicable disease | Social Services delivery | Health delivery | Conduct awareness on noncommendable diseases (Hypertension/ Diabetes) | District wide |  |  |  |  | 120,00 0.00 |  |  |  |  | DDHS | DNO |
|  |  | Health delivery | Organize screening on hypertension/ diabetes in 5 communities | District wide |  |  |  |  | 110,00 0.00 |  |  |  |  | DDHS | DNO |
| To ensure reduction of new HIV/AIDS, STIs and TB infections by 10% 31/12/2025 | Social Services delivery | Health delivery | HIV/AIDS awareness campaign in the communities | District wide |  |  |  |  | 50,000. 00 |  |  |  |  | DDHS/ DPHN | DCO /HP O/HI O |
|  |  |  | Conduct know your status campaign (KYSC) | District wide |  |  |  |  | 20,000. 00 |  |  |  |  | DDHS/ DPHN | DCO /HP O/HI O |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
|  |  |  | Observe world AIDS day | District wide |  |  |  |  | 60,000. 00 |  |  |  |  | DDHS/ DPHN | DCO /HP O/HI O |
|  |  |  | Ensure strict prevention Mother to Child Transmission of HIV | District wide |  |  |  |  | 20,000. 00 |  |  |  |  | DDHS/ DPHN/P HN | DCO /HP O/HI O |
|  |  |  | Ensure data management | District wide |  |  |  |  | 40,000. 00 |  |  |  |  | DDHS/ DPHN | DCO /HP O/HI O |
| Improve Tuberculosis case detection | Social services delivery | Health delivery | Train Tuberculosis coordinators and chemical sellers on case detection | District wide |  |  |  |  | 7,000.0 0 |  |  |  |  | DDHS | DDC O |
|  |  |  | Organize world Tuberculosis day | District wide |  |  |  |  | 15,000. 00 |  |  |  |  | DDHS | DDC O |
|  |  |  | Conduct health education on Tuberculosis at faith based institution | Faith based institutions |  |  |  |  | 60,000. 00 |  |  |  |  | DDHS | DDC O |
| Ensure 40% improvement in access to universal | Social Services delivery | Health delivery | Improve access to universal health coverage | District wide |  |  |  |  | 20,000. 00 |  |  |  |  | DDHS | DDC O |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
| health coverage (UHC) by Dec. 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ensure 30% improvement in food & nutrition security by Dec. 2025 | Social Services delivery | Health delivery | Train 50 community health nurses on management of acute malnutrition | District wide |  |  |  |  | 360,00 0.00 |  |  |  |  | DDHS | DNO |
| Ensure 20% Improvement in population management by Dec. 2025 | Social Services delivery | Health delivery | Train at least five (5) midwives on long term family planning methods | District wide |  |  |  |  | 400,00 0.00 |  |  |  |  | DDHS/ DPHN | PHN /CH NS BMC head s |
|  |  |  | Encourage proper data management of family planning services | District wide |  |  |  |  | 600,00 0.00 |  |  |  |  | DDHS/ DPHN | PHN /CH NS BMC head s |
|  |  |  | Conduct regular monitoring of health care delivery | District wide |  |  |  |  | 240,00 0.00 |  |  |  |  | DDHS/ DPHN | PHN /CH NS BMC head s |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  |  | Cost |  | Programme Status |  |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing |  | Lead | Colla b. |
| To increase skilled delivery by 5% | Social services delivery | Health delivery | Facilitate supervision to complicated labour | District wide |  |  |  |  | 320,00 0.00 |  |  |  |  |  | DDHS/ DPHN | MID WIV ES/B MC head s |
|  |  |  | Improve data management | District wide |  |  |  |  | 500,00 0.00 |  |  |  |  |  | DDHS/ DPHN | MID WIV ES/B MC head s |
|  |  |  | Provide logistics for complicated deliveries | District wide |  |  |  |  | 700,00 0.00 |  |  |  |  |  | DDHS/ DPHN | MID WIV ES/B MC head s |
| Water and Sanitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ensure 40% improvement in access to safe and reliable potable water supply by Dec. 2025 | Water and Environment al Sanitation | Water Management | Construction of 10 borehole | DUABONE, COLEMAN, OTABILKWAA AND ASAREKWAA |  |  |  |  | 142,370. 00 |  |  |  |  | DEHO/EH SU |  | WO RKS |
|  | Water and Environment al Sanitation | Water Management | Extension of pipe borne water | Nsaba New Site |  |  |  |  | 220,001. 90 |  |  |  |  | DEHO/EH |  | GW C |

| Objective | Programme (PBB) |  | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing |  | Lead | Colla b. |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SU |  |  |
| Ensure 50% access to improve sanitation services and management by Dec. 2025 ASGFGGS | Water and Environment al Sanitation |  | Sanitation Management | Implementation of community Led Total Sanitation (CLTS) | District wide |  |  |  |  | 10,000. 00 | 5,00 0.00 |  |  |  | DEHO/EH SU |  | DIC C &RI CCS |
|  |  |  |  | Support the construction of household toilets | Duabone,Kwek ukwaa, Ansakwaasel |  |  |  |  | 75,000. 00 | 10,0 00.0 0 |  |  |  | DEHO/EH SU |  | DIC C & RIC CS |
|  |  |  |  | Routine premises inspection | District wide |  |  |  |  | 7,000.0 0 | 1,00 0.00 |  |  |  | EHSU |  | Chief s and Unit com mitte e |
|  |  |  |  | Law enforcement /prosecution of sanitary offenders | District wide |  |  |  |  | 5,000.0 0 |  |  |  |  | EHSU |  | GPS |
|  | Water and Environment al Sanitation |  | Sanitation Management | Health education on cholera, malaria and corona virus in schools, churches, mosques and | District wide |  |  |  |  | 11,500. 00 |  |  |  |  | EHSU |  | GES/ GHS |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing |  | Lead | Colla b. |
|  |  |  | F.M stations. And clean ups |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Water and Environment al Sanitation | Sanitation Management | Clearing of refuse dump sites | District wide |  |  |  |  | 45,000. 00 |  |  |  |  | EHSU |  | Land field opera tors |
|  |  |  | Provision of refuse dump site | Seth Okai |  |  |  |  | 500,00 0.00 |  |  |  |  | EHSU |  | AED A/lan d field opera tors |
|  |  |  | Provision of zoomlion containers | Nsaba Salem |  |  |  |  | 250,00. 00 |  |  |  |  | EHSU |  | ZOO MLI ON |
|  |  |  | Celebration of National event | District wide |  |  |  |  | 30,000. 00 |  |  |  |  | EHSU, DCE & DCD |  | Chief s, Asse mply mem bers & GPS |
|  |  |  | Market inspection and sensitization on hygiene promotion | District wide |  |  |  |  | 5,000.0 0 |  |  |  |  | EHSU |  | MKT . Quee ns |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  |  | Cost |  | Programme Status |  |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing |  | Lead | Colla b. |
|  |  |  | Disinfection/disi nfestation of schools, market places, health facilities and sanitary sites | District wide |  |  |  |  | 110,00 0.00 |  |  |  |  | EHSU |  | Zoo mlio n |
|  |  |  | Purchase 300 pieces of 240 liters Dust bin | District wide |  |  |  |  | 30,000. 00 |  |  |  |  | Procureme nt Unit |  | DEH |
| Ensure 20% reduction in environmental pollution by Dec. 2025 | Water and Environment al Sanitation | Sanitation Management | Education on noise pollution and smoke nuisance | District wide |  |  |  |  | 3,000.0 0 |  |  |  |  | EHSU |  | CHI EFS |
|  |  |  | Enforcement sanitary laws | District wide |  |  |  |  | 5,000.0 0 |  |  |  |  | EHSU |  | GPS |
|  |  |  | Awareness creation on effect of water pollution | District wide |  |  |  |  | 6,000.0 0 |  |  |  |  | EHSU |  | CHI EFS |
| Social Welfare and Community Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Improve social protection services by 30% by Dec. 2025 | Social Services delivery | Social welfare and community development | Undertake leap payment and monitoring of beneficiaries | Leap communities |  |  |  |  | 1,200.0 0 | 1,80 0.00 | 3,000.00 |  |  |  | SWCD | CFPs /FPL s |
|  | Social Services delivery | Social Services delivery | Register PWDs on LEAP | Nsaba area council |  |  |  |  | 150,00. 00 | 100, 000. 00 | 50,000.0 0 |  |  |  | SWCD | CFPs /FPL s |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
|  | Social Services delivery | Social Services delivery | Assist aged, mentally ill patients and PWDs to access social services such as NHIS and acquisition of mobility equipment | Identified communities |  |  |  |  | 1,800.0 0 | 500. 00 | 2,300.00 |  |  | SWCD | NHI S/G HS |
|  |  |  | Undertake 750 home visit | District wide |  |  |  |  | 200.00 |  |  |  |  | SWCD | B&D , GES, CA MFE D GPS, TA |
| Reduce child rights abuse cases by 20% by Dec. 2025 | Social Services delivery | Social welfare and community development | To handle 32 child maintenance case by December 31, 2022 | Assembly hall (Agona Nsaba) |  |  |  |  | 715.00 |  |  |  |  | SWCD | B&D , GES, CA MFE D GPS, TA |
|  | Social Services delivery | Social welfare and community development | To Sensitize 10 selected basic schools on teenage | District wide |  |  |  |  | 110000 |  |  |  |  | SWCD | DA |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
|  |  |  | pregnancy |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Social Services delivery | Social Services delivery | To sensitize 10 selected community on the right of children, child neglect and child labour | Selected communities at Nsaba area council |  |  |  |  | 2,500.0 0 |  |  |  |  | SWCD | TA, DA |
|  | Social Services delivery | Social Services delivery | To monitor day care centres | Identified day care centres |  |  |  |  | 1500.0 0 |  |  |  |  | SWCD | TA, DA |
|  | Social Services delivery | Social Services delivery | To supervise and monitor orphanage home activities | Identified orphanage home |  |  |  |  | 1700.0 0 |  |  |  |  | SWCD | DA |
| Ensure economic improvement of persons with disabilities and vulnerable persons by 60% by Dec. 2025 | Social Services delivery | Social welfare and community development | To organize vocational and entrepreneurial skills training for PWDs | Nsaba and Asafo area council |  |  |  |  |  |  | 1,200.00 |  |  | SWCD | BAC |
|  | Social Services delivery | Social welfare and community development | To facilitate the disbursement of common fund to PWDs to engage them in various businesses, school fees payment and | District wide |  |  |  |  | 1,200.0 0 |  |  |  |  | SWCD | TA, DA |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
|  |  |  | start-ups |  |  |  |  |  |  |  |  |  |  |  |  |
| Ensure up to 20% participation of youth in districts development by Dec. 2025 | Social Services delivery | Social welfare and community development | To organize adult/mass education on nutrition, exclusive breastfeeding, health related issues and good life in 10 selected communities | District wide |  |  |  |  | 2,000.0 0 |  |  |  |  | SWCD | TA, DA |
| To promote gender mainstreaming through sensitization in all spheres of development by Dec. 2025 | Social Services delivery | Social welfare and community development | To sensitize 8 selected communities on the causes, form, effects and prevention of gender violence | Selected communities |  |  |  |  | 1,500.0 0 | 1,20 0.00 |  |  |  | Social welfare and commun ities develop ment | BAC |
|  | Social Services delivery | Social welfare and community development | To monitor Community Base Action Team | Kwansakrom,A gona Gyasikwaa,Me nsahkrom,Nam awura,Otwekro m, and Suromanya |  |  |  |  | 600.00 | 600. 00 |  |  |  | Social welfare and commun ities develop ment | AED A |
|  | Social Services delivery | Social welfare and community | To select and train ten (10) peer educations | SWESCCO, NSAS, NAMASCO, |  |  |  |  | 1,500.0 0 | 500. 00 |  |  |  |  | GHS /GES |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  |  | Cost |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
|  |  | development | for Senior High School in the districts on gender issues | and KWASTEC |  |  |  |  |  |  |  |  |  |  |  |
| Improve women empowerment by 40% by Dec. 2025 | Social Services delivery | Social welfare and community development | Organize entrepreneurial and vocational skills training programmes to selected women group | Selected communities welfare |  |  |  |  | 4,500.0 0 | 6,00 0.00 |  |  |  | SWCD | BAC |
| National Disaster Management Organization (NADMO) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To support the expansion of the district forest or tree cover by Dec. 2025 | Environment al and sanitation management | Disaster prevention and management | Education for community members on building on water ways in flood prone areas | District Wide |  |  |  |  | 2,500.00 | 1,00 0.00 | 1,500.00 |  |  | NADMO | DEH O, GNF S, AED A,, FC |
| To enhance climate change resilience | Environmental and sanitation management | Disaster prevention and management | Organize one (1) District Disaster Management Committee meeting. | District wide |  |  |  |  | 330.00 | 105. 00 | 225.00 |  |  | NADMO | DCE / NAD MO/ DEH O/G ES/P OLI CE /DPC |

| Objective |  | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  |  | Cost |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
|  |  |  |  | Tree planting during Green Ghana celebration | District wide |  |  |  |  | 1,500.0 0 | 500. 00 | 1,000.00 |  |  | NADMO | AED A/G ES |
|  |  |  |  | Public education on Domestic and Bush fires in the district | District wide |  |  |  |  | 3,060.0 0 | 1,00 0.00 | 2,060.00 |  |  | NADMO | GNF S, AED A,, FC |
|  |  |  |  | Establishment of 5000 capacity through tree planting and 2,500 cocoa nursery to farmers | District wide |  |  |  |  | 1,500.0 0 | 500. 00 | 1,000.00 |  |  | NADMO | AED A/G ES |
| Support the scale up of access to and adoption of efficient cook stoves to 5,000 by Dec. 2025 |  | Environmental and sanitation management | Disaster prevention and management | Desilting of gutters | District wide |  |  |  |  | 2,000.0 0 | 500. 00 | 1,500.00 |  |  | NADMO | DA |
| Department of Works |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Expand and improve road/transport infrastructure & services by 20% by Dec. 2025 |  | Infrastructure delivery and management | Infrastructure development | Reshaping of roads | Fantse Bawjiase To Akwakwaa, Kofikum- MansofoMensakrom, Agona Nsaba, Kokoado To Asarekwaa To |  |  |  |  |  |  | 400,000. 00 |  |  | WOR KS | Fee der Roa ds dept . |

| Objective | Programme (PBB) |  | Subprogramme |  | Activities |  |  | Location |  | Time Frame |  |  |  |  |  |  | Cost |  |  | Programme Status |  |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 | GoG | IGF | Others | New |  | Ongoing | Lead | Colla b. |
|  |  |  |  |  |  |  |  | Osedu To Kokroko To Ankomah To Akwakwaa, Nsaba To Duakwa To Jacob, Duabone To Kwesikum, Ninta To Nampong |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CB RD P |
| Provide adequate training for motorists and road users by Dec. 2022 | Infrastructure delivery and management |  | Road safety and management |  | Quarterly Education commercial Drivers defensive driving |  | of on | District wide |  |  |  |  |  |  |  |  | 1,000,00 0.00 |  |  |  |  |  | AEDA | CA/ WOR KS/M TTD |
|  |  |  |  |  | Support to MTTD to enforce motor traffic regulation |  |  | District wide |  |  |  |  |  |  |  |  | 34,000.0 0 |  |  |  |  |  | CA | MTT D |
|  |  |  |  |  | Replacement and repairs of broken down road signs. |  |  | District wide |  |  |  |  |  |  |  |  | 1,000,00 0.00 |  |  |  |  |  | CA | WOR KS |
|  |  |  |  |  | Provision of reflectors to Aboboyaa rider |  |  | District wide |  |  |  |  |  |  |  |  | 34,000.0 0 |  |  |  |  |  | CA | WOR KS/C A |
|  |  |  |  |  | Capacity building for Okada riders on road traffic regulations |  |  | District wide |  |  |  |  |  |  |  |  | 1,000,00 0.00 |  |  |  |  |  | CA | MTT D |
| Department of Physical Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Programme (PBB) |  | Subprogramme |  | Activities |  |  | Location |  | Time Frame |  |  |  |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
|  |  |  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 | Q4 | GoG | IGF | Others |  | New | Ongoing | Lead | Colla b. |
| Promote orderly development of human settlements |  | Infrastructure delivery and management |  | Physical and spatial planning |  | Prepare planning scheme for selected communities |  |  | Agona Nsaba |  |  |  |  |  |  |  | 5,000.0 0 | 2,00 0.00 | 7,000.00 |  |  |  | Cent. A | Physi cal Plan n. |
| To promote efficient and effective land administration |  | Infrastructure delivery and management |  | Physical and spatial planning |  | Conduct Street naming & property addressing |  |  | Agona Nsaba |  |  |  |  |  |  |  | 3,000.0 0 | 1,00 0.00 | 4,000.00 |  |  |  | Cent. A | Physi cal Plan n. |
| Support the acquisition of land banks for industrial development by Dec. 2025 |  | Infrastructure delivery and management |  | Physical and spatial planning |  | Acquire & demarcate for industrial development |  |  | Agona Nsaba |  |  |  |  |  |  |  | 5,000.0 0 | 1,00 0.00 | 6,000.00 |  |  |  | Cent. A | Physi cal Plan n. |
| Promote well development through 90% permitting of building applications by 2025 |  | Infrastructure delivery and management |  | Physical and spatial planning |  | Conduct sensitization on building permit requirements |  |  | District wide |  |  |  |  |  |  |  | 2,000.0 0 | 2,00 0.00 | 4,000.00 |  |  |  | Cent. A | Physi cal Plan n. |
| HUMAN RESOURCE DEPARTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training on service delivery standards and local government protocols |  | Capacity building |  | Human Resource development |  | To provide the staff with quality amenities to be able to acknowledge the service |  |  | Assembly Hall |  |  |  |  |  |  |  |  |  | 3,000 |  |  |  | HR | AED A |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
| Training area council functionaries on the operationalizati on of area councils | Capacity building | Human Resource development | To ensure the operationalizatio n of newly inaugurated area councils in the district | Assembly Hall |  |  |  |  |  |  | 5,500 |  |  | HR | AED A |
| Organization training workshop to train staff on interpersonal relation and customer service care | Capacity building | Human Resource development | To ensure officers interrelate cordially with each other to promote effective operation of the assembly | Assembly Hall |  |  |  |  |  |  | 9,700.00 |  |  | HR | AED A |
| Training on procurement act and procurement process | Capacity building | Human Resource development | To support and enhance effective and efficient running of the procurement management process | Assembly Hall |  |  |  |  |  |  | 10,178.0 0 |  |  | HR | AED A |
| Training on GIFMIS for revenue, Budget ,Account and Procurement staffs | Capacity building | Human Resource development | To help and strengthen the effectiveness and efficiency of budget, Revenue, Procurement and Account unit by Dec. | Assembly Hall |  |  |  |  |  |  | 3,000 |  |  | HR | AED A |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
|  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  |  |  |
| To build the capacity of staff with good records keeping, filing and saving document | Capacity building | Human Resource development | Training staff on records keeping, referencing, coding and filing of document | Assembly Hall |  |  |  |  |  |  | 12,100 |  |  | HR | AED A |
| Department of Central Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Strengthening of Sub-District Structures | District wide |  |  |  |  | 53,500. 00 | 23,0 00.0 0 | 30,500.0 0 |  |  | CA | AED A |
| Improve fiscal decentralization through 20% improvement in revenue mobilization | Management and administratio n | Finance and administratio n | Develop revenue improvement plan | Agona Nsaba |  |  |  |  | 5,000.0 0 | 1,50 0.00 | 500.00 |  |  | AEDA | CA |
|  |  |  | Identify new revenue areas | District wide |  |  |  |  | 2,000.0 0 | 1,00 0.00 | 500.00 |  |  | AEDA | CA |
|  |  |  | Recruite revenue collectors and bond them | District Wide |  |  |  |  |  |  |  |  |  | AEDA | CA |
| Improve popular participation through stakeholder engagements at all sub-structure levels | Management and administratio n | Planning Budgeting and Coordination | Conduct General Assembly meetings | District wide |  |  |  |  |  |  |  |  |  | AEDA | CA |
|  |  |  | Conduct Sub- Committee meetings | Agona nsaba |  |  |  |  | 53,500. 00 | 23,0 00.0 0 | 30,500.0 0 |  |  | CA | AED A |
|  |  |  | Conduct town hall meetings | District wide |  |  |  |  | 24,000. 00 | 4,00 0.00 | 5,000.00 |  |  | CA | AED A |
| Improve popular participation | Management and | Planning Budgeting | Conduct DPCU | Agona nsaba |  |  |  |  |  | 8,00 0.00 |  |  |  | CA | AED |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
| through stakeholder engagements at all sub-structure levels | administratio n | and Coordination | meetings |  |  |  |  |  |  |  |  |  |  |  | A |
|  |  |  | Conduct projects monitoring | District wide |  |  |  |  | 16,000. 00 | 8,00 0.00 |  |  |  | CA | AED A |
|  | Management and administratio n | Planning Budgeting and Coordination | Prepare Annual Plan & Budget |  |  |  |  |  | 35,000. 00 | 15,0 00.0 0 |  |  |  | CA | AE DA |
| Promote public safety and security | Management and administratio n | General administratio n | Maintenance of security | District wide |  |  |  |  | 30,000. 00 | 10,0 00.0 0 |  |  |  | Police/ others | CA |
| Promote access to justice delivery by Dec. 2025 | Management and administratio n | General administratio n | Construction of Police Station (Phase one and two) | Nsaba |  |  |  |  |  |  | 302,613. 00 |  |  | DWD | CA |
| To promote culture and tourism development by Dec. 2025 | Management and administratio n | General administratio n | Support the Organization of Central Regional District exhibition(EXP O’22) | Cape Coast |  |  |  |  |  |  | 10,000.0 0(DACF) |  |  | RCC | MM DA |
|  |  |  | Support the Organization of National festival of Act and | Cape Coast |  |  |  |  |  |  | 4,000.00 |  | DACF | CNC | CA/ RCC |

| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  |  | Cost |  | Programme Status |  | Implementing Inst. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
|  |  |  | Culture(NAFAT ) |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Support the organization of Akwambo festival | District wide |  |  |  |  |  | 10,0 00 |  |  |  | CA | AE DA |
| Emergency Planning and Response (Including Covid-19 Recovery Plan) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To develop capacity to mitigate disasters through creation of safety buffer zones | Environment al and sanitation management | Disaster prevention and management | Establish buffer zones in disaster prone areas | Nsaba area council |  |  |  |  | 12,00 0.00 |  |  |  |  | DEHO/ EHSU | Zoo mlio n |
| Enhance surveillance to prevent, detect, contain and respond to possible epidemic outbreak | Social Services delivery | Health delivery | Establish emergency centres | Nsaba health center |  |  |  |  | 360,00 0.00 |  |  |  |  | DDHS | DNO |
| Strengthen acute emergency care services for disaster situations | Social Services delivery | Health delivery | Train health staff in emergency case detection | Nsaba area council |  |  |  |  | 360,00 0.00 |  |  |  |  | DDHS | DNO |
| Establish a well resources emergency centre by Dec. 2025 | Social Services delivery | Health delivery | Resource established emergency centre | Nsaba area council |  |  |  |  | 460,00 0.00 |  |  |  |  | DDHS | DNO |
| Objective | Programme (PBB) | Subprogramme | Activities | Location | Time Frame |  |  |  |  | Cost |  | Programme Status |  | Implementing Inst. |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Colla b. |
| Implementation, Coordination, Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ensure resource mobilization improvement for plan implementation | Management and administratio n | General administratio n | Develop revenue improvement plan | Agona Nsaba |  |  |  |  | 12,00 0.00 |  |  |  |  | AEDA | CA |
| Strengthen planning capacities at all levels by Dec. 2025 | Management and administratio n | General administratio n | Train officers in planning and budgeting | Agona Nsaba |  |  |  |  | 360,00 0.00 |  |  |  |  | AEDA | CA |
| Strengthen Monitoring & Evaluation capacity at all levels by Dec. 2025 | Management and administratio n | General administratio n | Train officers in monitoring and evaluation | Agona Nsaba |  |  |  |  | 360,00 0.00 |  |  |  |  | AEDA | CA |
| Ensure investment in human capacity development and office infrastructure | Management and administratio n | General administratio n | Support capacity development of staff | Agona Nsaba |  |  |  |  | 460,00 0.00 |  |  |  |  | AEDA | CA |